# 6-Week MVP Project Plan

# 6-Week MVP Project Plan

## Mobile Recipe App · Vibe Coding Guardrails Included

## MVP Objective

Deploy a functional MVP mobile app in 6 weeks that proves the core user loop:

Open app → browse recipes → search/filter → view recipe → follow guided cooking steps → save/share recipe.

The MVP should not attempt to build the full PRD. The goal is a working, testable, cohesive app, not a feature-heavy app with disconnected or unstable pieces.

# MVP Must-Haves

- App project setup and shared development workflow

- Core app navigation

- Recipe library

- Recipe detail page

- Basic recipe data structure

- Recipe ingredients and steps

- Search and filters

- Guided cooking mode

- Saved recipes

- Share recipe functionality

- Loading, empty, and error states

- Basic content update process

- Internal testing build

- Final MVP build and handoff documentation

# Deferred From MVP

- Full account system

- Full onboarding survey

- Serving size and macro scaling

- Ratings/comments

- Admin analytics dashboard

- QR deep linking after install

- Web recipe landing pages

- Discovery/swipe mode

- Push notifications

- Loyalty, rewards

# Operating Rules for Vibe Coding

These rules apply every week.

## 1. You can vibe code features, not architecture

The team may use AI to code, debug, explain, and test, but they cannot independently change:

- App architecture

- Folder structure

- Data model

- Navigation structure

- Naming conventions

- Shared components

- Styling system

- Package dependencies

Architecture decisions must be approved by the technical lead or PM.

## 2. One source of truth

Before coding, the team must align on:

- App screens

- Data model

- Folder structure

- Shared components

- Design system

- Task board

- Pull request process

- Definition of done

No one should create duplicate versions of the same component or invent new data fields without approval.

## 3. One ticket = one pull request

Every pull request must map to one task only.

Good examples:

- Build recipe card component

- Add recipe detail screen

- Add dietary filter chips

- Add guided mode next/back navigation

Bad examples:

- Build recipe app

- Update all frontend

- Refactor everything

- AI changes

## 4. No direct commits to main

All work must happen in branches. Main should always be stable and demoable.

## 5. No test, no merge

Each pull request must include proof that it works:

- Screenshot or screen recording

- Manual test checklist

- Notes on edge cases tested

- Confirmation that the app runs locally

Automated tests are ideal, but for this MVP, every feature at minimum needs a manual QA checklist.

## 6. No package installs without approval

AI tools often suggest unnecessary packages. No new package or dependency can be added without approval from the integration lead.

## 7. No broad AI refactors

Do not ask AI to rewrite, restructure, optimize, or refactor the app broadly. AI should be used for specific tickets and specific bugs.

Allowed:

- Build this component

- Fix this bug

- Add this empty state

- Connect this screen to this data

Not allowed:

- Refactor the app

- Restructure the project

- Replace navigation

- Rename shared fields

- Rewrite all styling

## 8. Every intern must understand their code

AI-generated code is allowed, but the intern must be able to explain:

- What changed

- Why it changed

- What files were touched

- How they tested it

- What could break

Claude Code Security Best Practices Review Here

# Team Ownership Proposal (To be set in Week 2)

## Gina / Carolyn

Scope, backlog, QA, and launch decisions
Owns MVP prioritization, acceptance criteria, task board, QA plan, tester feedback, scope control, and final launch readiness.

## Freya

Backend / data and integration lead 
Owns recipe data structure, backend setup, data fetching, content workflow, media paths, and data documentation. Also makes sure all code works together, reviews technical consistency, watches for duplicate work, and protects main.

## Steven

Recipe library frontend
Owns recipe list, recipe cards, filter UI styling, and recipe library layout.

## Connor

Navigation / integration / build support
Owns app navigation, search, share flow, build troubleshooting, and weekly integration support.

## Josephine

Recipe detail and guided mode
Owns recipe detail page, ingredient list, guided cooking steps, checklist, and next/back flow.

## Jacqueline

Shared components and saved recipes
Owns reusable UI components, saved recipes, empty states, loading states, error states, and visual polish.

## Designer - TBD

Design system and design QA
Owns Figma, high-fidelity screens, component specs, visual QA, spacing, typography, and interaction notes.

# Required Pull Request Template

Every PR must include:

## What this PR does

Brief summary of the feature or fix.

## Ticket

Link to the assigned task.

## Screens/components changed

List files or screens touched.

## How I tested it

- [ ] App runs locally

- [ ] I tested the happy path

- [ ] I tested empty/error states if relevant

- [ ] I attached screenshots or a screen recording

## AI usage

What did AI help with?

## What I personally verified

Explain the code in your own words.

## Risks or questions

Anything the reviewer should pay attention to?

# Week 1: Competitive Audit, MVP Scope, Setup, and Engineering Rules

## Goal

Use the existing draft structure here for competitive audit to learn more about features and functions and find alignment on best in class execution of features.

## In Weekly Meeting

- Review full app vision

- Confirm MVP scope

- Confirm deferred features

- Assign team ownership

- Confirm integration lead

- Set up shared workspace, task board, code repository, and design workspace

- Review vibe coding rules

- Review PR process and definition of done

## Outside This Meeting

## Everyone (except designer)

Complete a focused competitive audit. Each person takes 5 references in two categories and captures:

- Screenshots

- What works

- What creates friction

- Recipe library patterns

- Recipe detail patterns

- Search/filter patterns

- Guided cooking patterns

- Save/share patterns

## PM

- QA of document to make sure it is consistent

## Designer

- Create lo-fi wireframes using existing template in Figma

## Week 1 Deliverables

- Focused competitive audit

- Engineering rules document

- PR template

- Initial app project

- Draft data model

- Lo-fi wireframes

## Week 1 Exit Criteria

The project is set up, everyone can run it, the MVP scope is locked, and no one starts building without shared rules.

# Week 2: Wireframes, Technical Recommendation, Data Structure, and App Skeleton

## Purpose

Finalize how the app should be structured. Build the app skeleton early to avoid integration issues in Week 4 or 5.

## In Weekly Meeting

- Review competitive audit takeaways

- Review lo-fi wireframes

- Confirm Week 2 design screens

- Review shared data model

## Outside This Meeting

## Technical Team

Create a technical recommendation document that describes the platform/tool each feature must support:

- Mobile app development

- Database/backend

- Recipe content storage

- Image/media storage

- Search/filtering

- Saved recipe state

- Build/deployment process

- Error monitoring

- Analytics, if included

Document:

- Options evaluated

- Recommendation

- Cost

- Complexity

- Risks

- MVP vs. later-phase needs

## Designer

Create high-fidelity MVP screens v1:

- To be Determined which screens to handoff

- Design System: Provide spacing, type, component, and interaction notes

## Frontend Team

TBD

- Build app shell

- Build navigation

- Build placeholder screens

- Build shared components

- Build recipe card

- Render recipes from sample data

## Backend/Data

TBD

- Finalize recipe data structure

- Add sample recipes

- Define recipe ingredients and steps

- Define tags for filters

- Document how content is added or edited

## PM

- Update backlog

- Confirm acceptance criteria

- Keep stretch features out

- Start QA checklist/ Testing Document

## Week 2 Deliverables

- High-fidelity MVP screens v1

- Technical recommendation document

- Working app skeleton

- Shared component list

- Final recipe data model v1

- Updated MVP backlog

## Week 2 Exit Criteria

The app opens, navigation works, recipe cards render, and the team has one shared data model.

# Week 3: Core Build — Recipe Library, Detail, Search/Filters, and Guided Mode

## Purpose

Build the core user loop. This is the most important development week.

## In Weekly Meeting

- Demo app skeleton

- Review designs

- Confirm owners by feature

- Review open blockers

- Confirm what must be merged by Friday

## Outside This Meeting

## Designer

- Finalize MVP design handoff

- Mark non-MVP designs as future phase

## Frontend Team

TBD

- Take updated high-fidelity designs and implement them

## Backend/Data

- Connect app to structured recipe data

- Create fetch/query functions

- Make sure recipe fields match the approved data model

- Add enough recipe records for testing

## Steven

TBD

- Build recipe library

- Build recipe cards

## Connor

TBD

- Build recipe detail page

- Build navigation refinements

- Support data integration

## Josephine

TBD

- Build filter UI

- Build search behavior

- Build guided cooking step flow

- Build ingredient checklist

## Jacqueline

TBD

- Build shared UI components

- Build saved recipes

- Build loading, empty, and error states

## PM

- Run QA on merged work

- Track bugs

- Enforce small PRs

- Stop duplicate components

- Review whether anyone is blocked

## Week 3 Deliverables

- Recipe library working

- Recipe detail working

- Search started

- Filters started

- Guided mode working

- Saved recipes started

- Design handoff complete

- Bug log started

## Week 3 Exit Criteria

A user can browse recipes, open a recipe, and move through guided steps.

# Week 4: Internal Build, Integration, QA, and Polish

## Purpose

Turn the working prototype into something testable by non-developers. This week is about integration, stability, and usability.

## In Weekly Meeting

- Demo core flow

- Review bugs

- Review design QA

- Confirm launch blockers

- Freeze MVP scope

- Assign testers

## Outside This Meeting

## All Developers

- Fix integration issues

- Reduce duplicate code

- Complete assigned MVP tickets

- Add screenshots or screen recordings to PRs

- Retest after merges

## Designer

- QA implementation against design

- Log must-fix visual issues

- Prioritize visual fixes

## Backend/Data

- Fix broken recipe records

- Confirm image/media paths

- Confirm filters return correct recipes

- Document content update process

## PM

- Prepare user testing script

- Triage bug log

- Confirm no new features are added

## Week 4 Deliverables

- Internal MVP build v1

- Working search/filter flow

- Working guided cooking flow

- Working saved/share flow

- Design QA log

- Bug log

- User testing script

## Week 4 Exit Criteria

A non-developer can open the app and complete the core flow without help.

# Week 5: User Testing, Bug Fixes, and Stabilization

## Purpose

Stop building new features. Test, fix, and stabilize.

## In Weekly Meeting

- Review internal build

- Review user testing plan

- Triage bugs

- Assign launch blockers

- Confirm what gets cut if time runs short

## Outside This Meeting

## User Testing

Each tester should:

- Open the app

- Find a recipe

- Use search or filters

- Open recipe detail

- Start guided cooking

- Move through steps

- Save a recipe

- Share a recipe

- Explain what felt confusing

## Developers

Fix bugs by severity:

- Launch blockers

- Important usability bugs

- Design inconsistencies

- Nice-to-have polish

## Designer

- Review tester feedback

- Identify UX blockers

- Support quick design fixes only

## PM

- Own bug triage

- Track retesting

- Confirm all must-have flows have been tested

- Start final handoff documentation

## Week 5 Deliverables

- User testing summary

- Prioritized bug log

- MVP release candidate

- Content QA complete

- Launch blocker list

## Week 5 Exit Criteria

At least 3 testers have used the app, launch blockers are known, and the app is stable enough for final QA.

# Week 6: Final QA, Final Build, Deployment, and Handoff

## Purpose

Finalize the MVP. No new features unless required to fix a launch blocker.

## In Weekly Meeting

- Review release candidate

- Review open blockers

- Confirm final build plan

- Review handoff documents

- Confirm Phase 1.5 backlog

## Outside This Meeting

## Final QA Checklist

Test:

- App opens

- Navigation works

- Recipe library loads

- Recipe cards display correctly

- Search works

- Filters work

- Recipe detail opens

- Ingredients display correctly

- Steps display correctly

- Guided mode works

- Save works

- Saved recipes display

- Share works

- Loading states work

- Empty states work

- Error states work

- App does not crash during core flow

## Developers

- Fix final launch blockers

- Prepare final build

- Clean up environment settings

- Document how to run and build the app

- Document known issues

## Designer

- Final visual QA

- Final screenshot support

- Confirm brand consistency

## Backend/Data

- Confirm recipe data is clean

- Confirm content update process works

- Confirm permissions and sensitive data are safe

## PM

- Run final acceptance testing

- Write release notes

- Complete known issues list

- Organize Phase 1.5 backlog

- Decide whether MVP is ready to deploy, demo, or continue testing

## Week 6 Deliverables

- Final MVP build

- Final QA checklist

- Technical handoff document

- Content handoff document

- Product handoff document

- Known issues list

- Phase 1.5 backlog

## Week 6 Exit Criteria

The app is demoable end-to-end, the core recipe flow works, the codebase is organized, known issues are documented, and the next phase is prioritized.

# MVP Definition of Done

The MVP is done when:

- A user can open the app

- A user can browse recipes

- A user can search/filter recipes

- A user can open a recipe

- A user can view ingredients and steps

- A user can follow guided cooking mode

- A user can save a recipe

- A user can revisit saved recipes

- A user can share a recipe

- Loading, empty, and error states exist

- Recipe content can be updated through a documented process

- The app is stable enough for internal testing or submission

- Known bugs are documented

- Deferred features are organized into the next-phase backlog

# Phase 1.5 Backlog

- Account creation

- Cloud-synced saved recipes

- Step videos or GIFs

- Basic analytics

- Basic onboarding questions

- Recipe hearts

- Post-cook feedback

- Improved recommendations

- QR landing flow improvements

- App store polish

# Best-Practice Summary

To avoid a junk app, the team must follow these principles:

- One architecture

- One data model

- One design system

- One shared component library

- One ticket per PR

- No direct commits to main

- No broad AI refactors

- No unapproved dependencies

- No merge without testing proof

- Daily integration

- Friday demos only from merged code

- Scope discipline over feature quantity

The goal is not to ship the most features. The goal is to ship the smallest version of the app that actually works together.